## Sheet1
Activity ID | Department | Work package | Activity | Dependency | Time(Days) | Critical Path
1 | Frontend | Normal Interface | Login & Register | 7 | 2 | 9 | 2 | Backend | RESTful Endpoint | Report
2 | Frontend | Normal Interface | Report & Report Event | 9 | 3 | 34 | 1 | Documents | Communicating | Google Docs
3 | Frontend | Normal Interface | Comment | 9 | 1 | 39 | 5 | Data Extraction | OAU | Outbreak Identifier
4 | Frontend | Map Interface | Design |  | 2 | 40 | 1 | Data Extraction | OAU | JSON Client
5 | Frontend | Map Interface | Pins |  | 4 |  | 9
6 | Frontend | Map Interface | Normal Interface Components Integration | 2 | 2
7 | Backend | RESTful Endpoint | JSON Web Token |  | 0
8 | Backend | RESTful Endpoint | Article |  | 2
9 | Backend | RESTful Endpoint | Report |  | 2
10 | Backend | RESTful Endpoint | Report Event |  | 2
11 | Backend | Servers | PostgreSQL | 7 | 1
12 | Backend | Servers | Django | 7 | 1
13 | Backend | Servers | Vue |  | 1
14 | Backend | Servers | Scraper |  | 2
15 | Backend | Servers | NLPE | 14 | 1
16 | Scraper | Scrapy | API Indexing |  | 2
17 | Scraper | Scrapy | API Page Parser |  | 3
18 | Scraper | Scrapy | Pipeline and Store Items | 8 | 1
19 | Management | GitHub | Iteration Tracking & Release Control |  | 1
20 | Management | GitHub | Code Quality Control |  | 1
21 | Management | GitHub | Documenting |  | 1
22 | Management | Planning | WBS |  | 1
23 | Management | Planning | Critical Path | 22 | 1
24 | Management | Planning | Use Cases |  | 2
25 | Management | Planning | User Story |  | 3
26 | Documents | Deliverable | Management Information |  | 1
27 | Documents | Deliverable | Design Detail |  | 2
28 | Documents | Deliverable | Testing Documentation |  | 2
29 | Documents | Deliverable | App Documentation |  | 2
30 | Documents | Deliverable | Final Report | 33 | 4
31 | Documents | Communicating | API Doucments | 11 | 1
32 | Documents | Communicating | Readmes |  | 2
33 | Documents | Communicating | Google Docs |  | 5
34 | Data Extraction | NLPE | Chunking |  | 1
35 | Data Extraction | NLPE | Context Understanding | 34 | 3
36 | Data Extraction | NLPE | Date Parse | 35 | 2
37 | Data Extraction | NLPE | Disease Parse | 36 | 2
38 | Data Extraction | NLPE | JSON Client | 9 | 1
39 | Data Extraction | OAU | Outbreak Identifier | 38 | 5
40 | Data Extraction | OAU | JSON Client | 39 | 1
|  |  |  | Finished | -11
|  |  |  | Total | 65
|  |  |  | Work Weeks | 13